## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Brittney | David | Evan | Ashish | Tyler | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task
Parallel Tasks | Architecture |  |  |  |  | 2 |  | 9
|  | Design architecture | Project Manager | Evan, Tyler, Brittney | 2 |  | 9 |  | 3 |  | 3 |  | 3 | 9
| Requirements |  |  |  |  | 13 |  | 15
|  | Gather | Developer | Evan, Tyler, Brittney | 3 |  | 6 |  | 2 |  | 2 |  | 2 | 6
|  | Analyze | Developer | Evan, Brittney | 4 |  | 3 |  | 1 |  | 2 |  |  | 3
|  | Specify | Developer | Brittney, David, Evan | 6 |  | 6 |  | 2 | 2 | 2 |  |  | 6
| Documentation |  |  |  |  | 11 |  | 13
|  | Project Charter | Developer | Brittney, David | 2 |  | 2 |  | 1 | 1 | 0 |  |  | 2
|  | Requirements Document | Project Manager, Developer | Brittney, David, Ashish, Evan | 6 |  | 8 |  | 1.5 | 1.5 | 4 | 1.5 |  | 8.5
|  | Project Plan | Project Manager, Developer | David, Brittney, Ashish | 3 |  | 3 |  | 0 | 0 | 0 | 1 |  | 1
Iteration 1: | Development |  |  |  |  | 15 |  | 33
|  | Determine technology needs | Developer | Brittney, Evan, Tyler | 3 |  | 4 |  | 1 |  | 1.5 |  | 1.5 | 4
|  | Research and learn new language and environment | Developer | Brittney, Ashish, David | 10 |  | 28 |  | 3 | 1 |  | 22 |  | 30
|  | Initial project setup | Project Manager | Evan | 2 |  | 1 |  |  |  | 1 |  |  | 1
| Analysis |  |  |  |  | 3 |  | 4
|  | Iteration Closeout | Developer, Project Manager | Brittney, Evan, David | 2 |  | 2 |  | 1 | 1 | 1 |  |  | 2
|  | Next iteration evaluation | Project Manager | Evan | 1 |  | 2 |  | 1 |  | 1 |  |  | 1
Iteration 2: | Design |  |  |  |  | 3 |  | 2
|  | Website Wireframe | UI Designer, Developer | David, Brittney | 3 |  | 2 |  | 1 | 2 |  |  |  | 3
0
0
0
0
| Documentation |  |  |  |  | 10 |  | 11.5
|  | Project Plan | Project Manager, Developer | Brittney, Evan, David | 3 |  | 4 |  | 2 | 1 |  |  |  | 3
|  | Risk Management Report | Project Manager, Developer | Brittney, Evan, David | 2 |  | 1.5 |  | 0.75 | 0.5 | 2 |  |  | 3.25
|  | Commerce Presentation |  | Brittney, Evan, David, Ashish | 5 |  | 6 |  | 2 | 1 | 2 | 1 |  | 6
0
0
| Analysis |  |  |  |  | 3 |  | 3.5
|  | Iteration Closeout | Developer, Project Manager | Brittney, Evan, David | 2 |  | 2.5 |  | 1 | 0.5 | 1 |  |  | 2.5
|  | Next iteration evaluation | Project Manager | Evan | 1 |  | 1 |  |  |  | 1 |  |  | 1
0
Iteration 3: | Design |  |  |  |  | 12 |  | 16
|  | Dashboard Design | UI Designer | Brittney, David | 6 |  | 8 |  | 4 | 3 |  |  |  | 7
|  | Register Component Design | UI Designer | Brittney, Ashish | 3 |  | 5 | [6 empty] | 0
|  | Login Component Design | UI Designer | Brittney, Evan | 3 |  | 3 | [6 empty] | 0
| Development |  |  |  |  | 24.5 |  | 19
|  | Set up Firebase Authentication and Firestore | Developer | Evan | 2 |  | 2 |  |  |  | 2 |  |  | 2
|  | Finished Setting up Development Environment | Developer | Evan | 1 |  | 2 |  |  |  | 2 |  |  | 2
|  | Setup Project Github Repo | Developer | Evan | 0.5 |  | 1 |  |  |  | 1 |  |  | 1
|  | Authentication and User Services | Database Designer | Tyler | 2 |  | - | [6 empty] | 0
|  | Project Tools Research | Developer | David, Brittney, Ashish | 5 |  | 10 |  | 2 | 4 |  | 2
|  | Dashboard Component | Developer | David | 6 |  | - |  |  | -
|  | Register Component | Developer | Ashish | 4 |  | - |  |  |  |  | -
|  | Login Component | Developer | Evan | 4 |  | 4 |  |  |  | 4 |  |  | 4
| Analysis |  |  |  |  | 2 |  | 2
|  | Iteration Closeout | Project Manager | Evan, Brittney, David | 2 |  | 2 |  | 1 | 0.5 | 0.5 |  |  | 2
|  | Next iteration evaluation | Project Manager | [10 empty] | 0
Iteration 4: | Design |  |  |  |  | 4 |  | 6
|  | App Theme, Element Styling | UI Designer | Brittney | 2 |  | 3 |  | 3 |  |  |  |  | 3
|  | Dashboard wireframe | Developer | Brittney | 2 |  | 3 |  | 3 |  |  |  |  | 3
|  | Login Component | Developer | Evan | 3 |  | 2 |  |  |  | 2
|  | Registration Component | Developer | Evan, Ashish | 4 |  | 3 |  |  |  | 3 | 1
|  | Transaction Component | Developer | David | 4 |  | 4 |  |  | 4
| Development |  |  |  |  | 13 |  | 11
|  | Project Tools Research | Developer | Brittney, David | 2 |  | 4 |  | 2 | 2 |  |  |  | 4
|  | Dashboard prototype integration | UI Developer | Brittney | 3 |  | 2 |  | 2 |  |  |  |  | 2
|  | Login Component | Developer | Evan | 3 |  | 3 |  |  |  | 3 |  |  | 3
|  | Registration Component and validation | Developer | Evan, Ashish | 5 |  | 2 |  |  |  | 2 | 2 |  | 4
| Analysis |  |  |  |  | 2 |  | 2
|  | Iteration 4 Evaluation | Project Manager | Evan, Brittney | 1 |  | 1 |  | 0.5 |  | 0.5 |  |  | 1
|  | Iteration 4 Estimated Effort | Project Manager | Evan, Brittney, David | 1 |  | 1 |  | 0.5 |  | 0.5 |  |  | 1
Iteration 5: | Design |  |  |  |  | 11 |  | 12
|  | Notifications Design | UI Designer | Brittney, Ashish | 4 |  | 4 |  | 4 | 3 |  |  |  | 7
|  | Transactions Design | UI Designer | David, Brittney | 4 |  | 4 |  | 2 | 2 |  |  |  | 4
|  | Additional Dashboard Design | UI Designer | Brittney | 3 |  | 4 |  | 4 |  |  |  |  | 4
| Development |  |  |  |  | 28 |  | 24
|  | Finish Firebase Authentication and Firestore | Developer | Evan | [6 empty] | 2 |  |  | 2
|  | Password Recovery Stretch Goal | Developer | Evan | [6 empty] | 2 |  |  | 2
|  | Authentication and User Services | Database Designer | Evan, Ashish | 4 | [6 empty] | 6 |  | 6
|  | Project Tools Research | Developer | David, Brittney, Ashish | 7 |  | 7 |  | 5 | 4 |  | 3
|  | Dashboard Component | Developer | David, Brittney, Ashish | 5 |  | 5 |  | 5 | 1
|  | Notification Component |  | Brittney, Evan | 4 |  | 4 |  | 4
|  | Registration Component |  | Ashish | 2 |  | 4 |  |  |  |  | 4
|  | Login Component |  | Brittney, Ashish | 2 | [6 empty] | 1
|  | Transaction Component | Developer | David, Brittney, Evan | 4 |  | 4 |  | 3 | 10 | 4 |  |  | 17
|  | Component Testing | Testing | Evan, Brittney, David, Ashish | 4 | [6 empty] | 2
| Analysis |  |  |  |  | 2 |  | 2
|  | Iteration 5 Closeout | Project Manager | Evan, Brittney, David | 1 |  | 1 |  | 1 | 0.5 | 0.5 |  |  | 2
|  | Iteration 5 Estimated Effort | Project Manager | Brittney, Evan | 1 |  | 1 |  |  |  |  | 0.5 |  | 0.5
Total | [5 empty] | 98.5 |  | 128 | 69.25 | 45.5 | 52.5 | 47 | 6.5 | 151.5