## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Brittney | David | Evan | Ashish | Tyler | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task
Parallel Tasks | Architecture |  |  |  |  | 2 |  | 9
|  | Design architecture | Project Manager | Evan, Tyler, Brittney | 2 |  | 9 |  | 3 |  | 3 |  | 3 | 9
| Requirements |  |  |  |  | 13 |  | 15
|  | Gather | Developer | Evan, Tyler, Brittney | 3 |  | 6 |  | 2 |  | 2 |  | 2 | 6
|  | Analyze | Developer | Evan, Brittney | 4 |  | 3 |  | 1 |  | 2 |  |  | 3
|  | Specify | Developer | Brittney, David, Evan | 6 |  | 6 |  | 2 | 2 | 2 |  |  | 6
| Documentation |  |  |  |  | 11 |  | 13
|  | Project Charter | Developer | Brittney, David | 2 |  | 2 |  | 1 | 1 | 0 |  |  | 2
|  | Requirements Document | Project Manager, Developer | Brittney, David, Ashish, Evan | 6 |  | 8 |  | 1.5 | 1.5 | 4 | 1 |  | 8
|  | Project Plan | Project Manager, Developer | David, Brittney, Ashish | 3 |  | 3 |  | 0 | 0 | 0 |  |  | 0
Iteration 1: | Development |  |  |  |  | 15 |  | 33
|  | Determine technology needs | Developer | Brittney, Evan, Tyler | 3 |  | 4 |  | 1 |  | 1.5 |  | 1.5 | 4
|  | Research and learn new language and environment | Developer | Brittney, Ashish, David | 10 |  | 28 |  | 1 | 1 |  | 22 |  | 28
|  | Initial project setup | Project Manager | Evan | 2 |  | 1 |  |  |  | 1 |  |  | 1
| Analysis |  |  |  |  | 3 |  | 4
|  | Iteration Closeout | Developer, Project Manager | Brittney, Evan, David | 2 |  | 2 |  | 1 | 1 | 1 |  |  | 2
|  | Next iteration evaluation | Project Manager | Evan | 1 |  | 2 |  | 1 |  | 1 |  |  | 1
Iteration 2: | Design |  |  |  |  | 0 |  | 0 | [5 empty] | 0
| Development |  |  |  |  | 0 |  | 0
| Analysis |  |  |  |  | 0 |  | 0
Iteration 3: | Design |  |  |  |  | 0 |  | 0
| Development |  |  |  |  | 0 |  | 0
| Analysis |  |  |  |  | 0 |  | 0
Total | [5 empty] | 44 |  | 74 | 14.5 | 6.5 | 17.5 | 23 | 6.5 | 53.5